tenXengage

AI-Powered Channel Revenue Outcomes

Redemption Store Integration

Development Delivery Process & Timeline

XTRM (Cash) · Xoxoday (Non-Cash) · Dual Wallet · Ledger Engine · Returns

| Feature: | Redemption Store Integration |
| --- | --- |
| Vendors: | XTRM (Cash) · Xoxoday (Non-Cash) |
| Timeline: | 14 Weeks · 6 Sprints · 2 Weeks Pre-Sprint |
| Tiers: | Starter · Professional · Enterprise |
| Version: | 1.0 — April 2026 |

Highly Confidential

# 1. Feature Overview

The Redemption Store Integration enables partner sellers and partner companies to redeem earned rewards across cash-based payouts (via XTRM) and non-cash rewards (via Xoxoday). TenXEngage owns the authoritative reward wallet ledger and the end-to-end user experience. Both vendors operate as fulfillment engines.

| Dimension | Detail |
| --- | --- |
| Feature | Redemption Store Integration |
| Cash Vendor | XTRM — ACH, PayPal, Venmo, international transfers (180+ countries) |
| Non-Cash Vendor | Xoxoday — gift cards, merchandise, prepaid cards, travel, events (100+ countries) |
| Wallet Model | Individual seller wallet + company pooled wallet, per currency type |
| Currency Types | Cash, Points, Credits, Tickets (4 types — no additions) |
| Ledger Model | Two-step: Reserve on submission, Debit on vendor COMPLETED webhook |
| Returns | Non-cash only, user-initiated, Client Admin approval, Xoxoday confirmation required |
| Tiers | Starter, Professional, Enterprise (all tiers enabled) |
| Total Timeline | 14 weeks from kick-off to production release |
| Sprint Structure | 2-week sprints. 2-week pre-sprint Technical Design. 6 sprints. |

# 2. Team Structure

| Role | Count | Assignments |
| --- | --- | --- |
| Product Manager | 1 | Owns BRD, resolves open questions, accepts stories, signs off on go-live |
| Tech Lead / Architect | 1 | Data model ownership, API contract design, XTRM and Xoxoday integration architecture, code review |
| Backend Engineer 1 (BE1) | 1 | Wallet engine, LedgerEntry, WalletService — Sprint 1 |
| Backend Engineer 2 (BE2) | 1 | Catalog service, RedemptionOrchestrationService, ClientRedemptionConfig, Returns service |
| Backend Engineer 3 (BE3) | 1 | XTRM adapter, Xoxoday adapter, webhook handlers, catalog sync |
| Frontend Engineer 1 (FE1) | 1 | Wallet dashboard, Redemption Store catalog page, Transaction History page |
| Frontend Engineer 2 (FE2) | 1 | Client Admin configurator, returns flow, admin approval queue, analytics dashboard |
| QA Engineer | 1 | Test plan, unit and integration test review, full E2E suite, Sprint 6 sign-off |
| DevOps | 0.5 | Staging environment, secrets manager, feature flag config, deployment pipeline |
| Delivery Lead | 0.5 | Sprint planning, dependency tracking, blocker escalation, milestone reporting |

# 3. Critical Dependencies

All dependencies below must be resolved before the sprint that first needs them. Any dependency not resolved by its required date must be escalated immediately to the Delivery Lead.

| Dependency | Required By | Owner | Action Required |
| --- | --- | --- | --- |
| XTRM sandbox API credentials and webhook test endpoint | Pre-Sprint Week 1 | Product Manager | Contact XTRM account manager. Confirm sandbox environment supports webhook delivery. |
| Xoxoday sandbox API credentials, catalog API, and return API access | Pre-Sprint Week 1 | Product Manager | Contact Xoxoday account manager. Confirm return API availability and webhook schemas. |
| XTRM webhook payload schema documentation | Pre-Sprint Week 2 | Tech Lead | Schedule technical API review session with XTRM during Pre-Sprint. |
| Xoxoday webhook payload schema (order, return events) | Pre-Sprint Week 2 | Tech Lead | Schedule technical API review session with Xoxoday during Pre-Sprint. |
| Staging database and secrets manager ready | Pre-Sprint Week 2 | DevOps | Confirm PostgreSQL 16 staging instance and secrets management service ready before Sprint 1. |
| Open Question #2 resolved — company wallet approval requirements | Sprint 2 end | Product Manager | Decision needed before company wallet redemption stories are pointed in Sprint 3. |
| Open Question #3 resolved — batch processing cadence configuration | Sprint 2 end | Product Manager | Decision needed before batch mode processing stories are pointed in Sprint 3. |
| Open Question #5 resolved — quantity-based vs amount-based non-cash | Sprint 1 end | Product Manager | Affects catalog item data model. Must be resolved before Sprint 2 catalog work begins. |

# 4. Delivery Phases and Sprint Plan

The delivery is structured across three phases: Pre-Sprint Technical Design, Build (Sprints 1–5), and Validation and Release (Sprint 6). All dates below are relative to Week 0 kick-off — adjust to your actual calendar start date.

PRE-SPRINT: TECHNICAL DESIGN ¦ Weeks 1–2

The Technical Design phase produces all the architecture artifacts engineering needs before writing a single line of code. Nothing in Sprint 1 starts until these outputs are reviewed and approved.

| Activity | Owner | Output | Done When |
| --- | --- | --- | --- |
| Finalize all six entity designs (RewardWallet, LedgerEntry, RedemptionCatalogItem, ClientRedemptionConfig, RedemptionTransaction, RedemptionReturn) | Tech Lead + BE1 + BE2 | Approved entity designs with field list, types, constraints, and index strategy | Tech Lead sign-off |
| Draft all Flyway migration SQL files V001–V009 | BE1 + BE2 | Migration SQL reviewed for index coverage, UUID defaults, and tenant scoping | Tech Lead review complete |
| Draft OpenAPI 3.0.1 contract for all 20 endpoints | Tech Lead | Signed-off API contract used as the interface agreement between BE and FE | Product Manager + Tech Lead sign-off |
| XTRM API integration design — request/response shapes, error handling, retry logic | BE3 | XTRM integration design document | Tech Lead review complete |
| Xoxoday API integration design — order, return, and catalog sync flows | BE3 | Xoxoday integration design document | Tech Lead review complete |
| Create full sprint backlog — all stories with estimates and dependencies mapped | Delivery Lead + Product Manager | Sprint-ready backlog in project management tool | Sprint 1 planning ready |
| Staging environment provisioned — PostgreSQL, secrets manager, feature flag service | DevOps | Staging environment accessible to all engineers | DevOps confirmation |

| Pre-Sprint Gate | Sprint 1 does not start until: entity designs are approved, API contract is signed off, vendor credentials are in hand, and staging environment is confirmed ready. |
| --- | --- |

SPRINT 1: WALLET ENGINE ¦ Weeks 3–4

Sprint 1 builds the foundation everything else depends on — the wallet model and the ledger engine. No redemption work can begin until these are live and tested in staging.

| Story | Description | Owner | Points |
| --- | --- | --- | --- |
| RS-001 | RewardWallet — JPA entity, Flyway migration V001, repository, optimistic locking | BE1 | 3 |
| RS-002 | LedgerEntry — JPA entity, Flyway migration V002, immutable write pattern | BE1 | 3 |
| RS-003 | WalletService — credit(), reserve() with pessimistic lock, debit(), release(), returnCredit(), idempotency | BE1 | 5 |
| RS-004 | WalletController — GET /wallets/me, GET /wallets/company/{id}, permission gates | BE1 | 2 |
| RS-005 | Feature flag seed migration V007 — redemption_store enabled for all 3 tiers | BE1 | 1 |
| RS-006 | Permission keys seed migration V008 — all 11 permission keys inserted | BE2 | 1 |
| RS-007 | Default role-permission mappings migration V009 | BE2 | 2 |
| RS-008 | WalletDashboard frontend page — per-currency balance cards, skeleton, empty state | FE1 | 3 |
| RS-009 | WalletBalanceWidget — persistent nav widget, feature flag + permission check | FE1 | 2 |
| RS-010 | WalletService unit tests — all balance mutation scenarios, InOrder ledger verification | QA + BE1 | 3 |

| Sprint 1 Exit Gate | Individual and company wallets display correct per-currency balances in staging. WalletService unit tests passing at 60%+ coverage. Ledger writes before balance updates verified by InOrder tests. Persistent balance widget visible in nav. |
| --- | --- |

SPRINT 2: CATALOG & CLIENT CONFIGURATION ¦ Weeks 5–6

Sprint 2 delivers the redemption catalog and tenant configuration layer. By end of Sprint 2, Client Admins can configure their catalog and partner sellers can browse currency-filtered redemption options.

| Story | Description | Owner | Points |
| --- | --- | --- | --- |
| RS-011 | RedemptionCatalogItem — entity, migration V003, global seed data from Xoxoday and XTRM | BE2 | 3 |
| RS-012 | ClientRedemptionConfig — entity, migration V004, unique constraint, config service | BE2 | 3 |
| RS-013 | RedemptionCatalogService — currency-aware filter, geographic filter, shortfall calculation, client config | BE2 | 5 |
| RS-014 | Catalog API — GET /catalog (currency-aware), GET /config, PUT /config — all with permission gates | BE2 | 3 |
| RS-015 | Xoxoday catalog sync — syncXoxodayCatalog() scheduled job, upsert and deactivate logic | BE3 | 3 |
| RS-016 | RedemptionStore frontend page — catalog browser, currency pre-filter from URL param, item cards | FE1 | 5 |
| RS-017 | RedemptionStore — unavailable items display with shortfall amount and disabled Redeem button | FE1 | 2 |
| RS-018 | Client Admin catalog configurator — enable/disable items, threshold config, processing mode override | FE2 | 3 |
| RS-019 | Regional catalog configuration — per-region item enablement in ClientRedemptionConfig | BE2 + FE2 | 5 |

| Sprint 2 Exit Gate | Currency-aware catalog browsing working correctly in staging for multiple currency types. Client Admin can enable/disable catalog items. Regional filtering applies correctly. Shortfall amount displays on unavailable items. |
| --- | --- |

SPRINT 3: REDEMPTION FLOW & VENDOR INTEGRATION ¦ Weeks 7–8

Sprint 3 is the core of the feature — end-to-end redemption submission, vendor routing, and the XTRM and Xoxoday adapter integrations. By end of Sprint 3, a redemption request travels from the UI all the way to the vendor sandbox.

| Story | Description | Owner | Points |
| --- | --- | --- | --- |
| RS-020 | RedemptionTransaction — entity, migration V005, all fields including providerName enum | BE2 | 3 |
| RS-021 | RedemptionOrchestrationService — eligibility validation, balance reservation, processing mode routing | BE2 | 5 |
| RS-022 | XtrmAdapter — submitPayout(), HMAC auth header, retry logic, VendorUnavailableException | BE3 | 5 |
| RS-023 | XoxodayAdapter — placeOrder(), retry logic, catalog sync method | BE3 | 5 |
| RS-024 | RedemptionController — POST /requests, POST /requests/company, GET /requests, GET /requests/{id} | BE2 | 3 |
| RS-025 | RedemptionController — POST /{id}/approve, POST /{id}/reject (APPROVAL_REQUIRED mode) | BE2 | 2 |
| RS-026 | RedemptionStore — RedemptionDrawer with amount input, processing mode description, SLA display | FE1 | 5 |
| RS-027 | RedemptionStore — submission flow, useSubmitRedemption mutation, success/error toast | FE1 | 3 |
| RS-028 | RedemptionOrchestrationService integration test — INSTANT, BATCH, APPROVAL_REQUIRED flows | QA + BE2 | 3 |

| Sprint 3 Exit Gate | Full end-to-end redemption submission working against XTRM and Xoxoday sandboxes in staging. Balance reserved on submission. APPROVAL_REQUIRED requests held before vendor handoff. Retry logic confirmed via sandbox error simulation. |
| --- | --- |

SPRINT 4: WEBHOOKS, TRANSACTION HISTORY & NOTIFICATIONS ¦ Weeks 9–10

Sprint 4 closes the redemption loop — vendor status updates flow back into TenXEngage, ledger entries are finalized, and users can track every transaction. By end of Sprint 4 all Track A (must-ship) requirements are complete.

| Story | Description | Owner | Points |
| --- | --- | --- | --- |
| RS-029 | XtrmWebhookService — HMAC-SHA256 verification, COMPLETED/FAILED/CANCELLED handling, idempotency | BE3 | 5 |
| RS-030 | XoxodayWebhookService — HMAC verification, FULFILLED/FAILED handling, idempotency | BE3 | 5 |
| RS-031 | Webhook controllers — POST /webhook/xtrm, POST /webhook/xoxoday, permitAll + HMAC in service | BE3 | 2 |
| RS-032 | Webhook integration tests — idempotency, invalid HMAC rejection, DB state assertions | QA + BE3 | 5 |
| RS-033 | Transaction history API — GET /requests (paginated, filtered), GET /requests/all, GET /requests/export | BE2 | 3 |
| RS-034 | TransactionHistory frontend page — filterable table, status badges, date range filter, export | FE1 | 5 |
| RS-035 | Observability — MDC fields (transactionId, walletId, vendorName), Micrometer counters, key log statements | BE1 + BE3 | 3 |
| RS-036 | Notifications — all redemption lifecycle events wired to NotificationCategory.REWARDS | BE2 | 3 |
| RS-037 | Payout SLA display — estimated delivery timeframe on catalog item and redemption confirmation | FE1 + BE2 | 2 |

| Track A Complete — Sprint 4 Exit Gate | All Track A acceptance criteria met: wallets live, catalog browsing correct, redemptions route to correct vendor, webhooks update ledger and transaction status, transaction history accessible and exportable, balance widget visible platform-wide, notifications sending, SLA timeframes displayed. |
| --- | --- |

SPRINT 5: RETURNS & ANALYTICS ¦ Weeks 11–12

Sprint 5 delivers Track B — the returns flow and Client Admin analytics dashboard. These are independent of production launch readiness but complete the full BRD scope before validation.

| Story | Description | Owner | Points |
| --- | --- | --- | --- |
| RS-038 | RedemptionReturn — entity, migration V006, one-to-one with RedemptionTransaction | BE2 | 3 |
| RS-039 | ReturnsService — submitReturnRequest(), approveReturn(), rejectReturn(), cancelReturn(), return window validation | BE2 | 5 |
| RS-040 | XoxodayAdapter — submitReturn(), VendorReturnRejectedException handling | BE3 | 3 |
| RS-041 | XoxodayWebhookService — RETURN_CONFIRMED and RETURN_FAILED event handling | BE3 | 3 |
| RS-042 | Returns API — all 5 endpoints: submit, list, approve, reject, cancel | BE2 | 3 |
| RS-043 | Return request frontend flow — submit from TransactionHistory, status tracking, cancel | FE2 | 3 |
| RS-044 | Admin return approval queue — pending returns list, approve/reject with reason | FE2 | 3 |
| RS-045 | Return notifications — all return lifecycle events wired | BE2 | 2 |
| RS-046 | Redemption rate analytics service — rate by currency type, catalog item, tier, region | BE2 | 5 |
| RS-047 | Unredeemed balance report — total outstanding liability by currency type | BE2 | 3 |
| RS-048 | Analytics dashboard frontend — redemption rate charts, unredeemed balance, filter by tier/region | FE2 | 5 |
| RS-049 | Returns integration tests — return window, Xoxoday rejection, wallet credit only on confirmation | QA + BE2 | 3 |

| Sprint 5 Exit Gate | Full returns flow end-to-end in staging: submit, approve, Xoxoday confirmation, wallet credited. Admin approval queue working. Analytics dashboard shows redemption rates. Unredeemed balance report exportable. |
| --- | --- |

SPRINT 6: VALIDATION & RELEASE ¦ Weeks 13–14

Sprint 6 is validation and release only — no new feature work. All stories from Sprints 1–5 must be accepted before Sprint 6 begins. The output of Sprint 6 is a production release.

| Activity | Owner | Days | Criteria |
| --- | --- | --- | --- |
| Full E2E test suite execution — all 5 Playwright scenarios plus regression | QA | 3 | All scenarios passing. Zero P1/P2 defects open. |
| Security review — tenant isolation, webhook HMAC auth, permission gates, no credentials in logs | Tech Lead + QA | 2 | Security review sign-off document produced. All findings resolved or risk-accepted. |
| Performance validation — wallet balance reads and webhook processing under load | Tech Lead + DevOps | 2 | Balance reads < 100ms at p95. Webhook processing handles 100 concurrent events without ledger inconsistency. |
| Bug fix and acceptance sprint | All BE + FE | 3 | All P1/P2 bugs from QA resolved. Product Manager accepts all open stories. |
| Production environment prep — migrations, secrets, feature flag, vendor webhooks registered | DevOps | 2 | All Flyway migrations applied to production. XTRM and Xoxoday webhook URLs pointing to production. |
| Go-live checklist completion | Delivery Lead + Product Manager | 1 | All 12 items on the go-live checklist signed off. |
| Release notes and support briefing | Product Manager | 1 | Release notes published. Support team briefed on new feature and known edge cases. |
| Production release — feature flag enabled per rollout plan | DevOps + Product Manager | 1 | Feature live in production. Monitoring dashboards active. Rollback plan confirmed. |

| Sprint 6 Exit Gate — Production Release | Go-live checklist fully checked. E2E suite passing. Security review signed off. Performance validated. Release notes approved. Rollback plan documented and tested. |
| --- | --- |

# 5. Full Story Backlog

All 49 stories across Track A (must ship) and Track B (returns and analytics). Story points use the Fibonacci scale. Nothing larger than 8 points — split any story estimated at 13+.

| ID | Story Title | Pts | Sprint | Depends On | Owner |
| --- | --- | --- | --- | --- | --- |
| RS-001 | [BE] RewardWallet — entity, migration V001, repository, optimistic locking | 3 | S1 | — | BE1 |
| RS-002 | [BE] LedgerEntry — entity, migration V002, immutable write | 3 | S1 | — | BE1 |
| RS-003 | [BE] WalletService — credit, reserve, debit, release, returnCredit, idempotency | 5 | S1 | RS-001, RS-002 | BE1 |
| RS-004 | [BE] WalletController — GET /wallets/me, GET /wallets/company/{id} | 2 | S1 | RS-003 | BE1 |
| RS-005 | [BE] Feature flag migration V007 — redemption_store all tiers enabled | 1 | S1 | — | BE1 |
| RS-006 | [BE] Permission keys migration V008 — all 11 keys | 1 | S1 | — | BE2 |
| RS-007 | [BE] Role-permission mappings migration V009 | 2 | S1 | RS-006 | BE2 |
| RS-008 | [FE] WalletDashboard page — per-currency cards, skeleton, empty state | 3 | S1 | RS-004 | FE1 |
| RS-009 | [FE] WalletBalanceWidget — persistent nav widget, feature flag check | 2 | S1 | RS-004 | FE1 |
| RS-010 | [QA] WalletService unit tests — InOrder ledger verification, all mutation scenarios | 3 | S1 | RS-003 | QA+BE1 |
| RS-011 | [BE] RedemptionCatalogItem — entity, migration V003, global seed data | 3 | S2 | — | BE2 |
| RS-012 | [BE] ClientRedemptionConfig — entity, migration V004, unique constraint, config service | 3 | S2 | RS-011 | BE2 |
| RS-013 | [BE] RedemptionCatalogService — currency-aware filter, geographic filter, shortfall | 5 | S2 | RS-011, RS-012 | BE2 |
| RS-014 | [BE] Catalog API — GET /catalog, GET/PUT /config with permission gates | 3 | S2 | RS-013 | BE2 |
| RS-015 | [BE] Xoxoday catalog sync — syncXoxodayCatalog(), upsert and deactivate | 3 | S2 | RS-011, Xoxoday creds | BE3 |
| RS-016 | [FE] RedemptionStore page — catalog browser, currency pre-filter from URL | 5 | S2 | RS-008, RS-014 | FE1 |
| RS-017 | [FE] RedemptionStore — unavailable items, shortfall display, disabled button | 2 | S2 | RS-016 | FE1 |
| RS-018 | [FE] Client Admin catalog configurator — enable/disable, thresholds, mode override | 3 | S2 | RS-014 | FE2 |
| RS-019 | [BE+FE] Regional catalog configuration — per-region item enablement | 5 | S2 | RS-012, RS-018 | BE2+FE2 |
| RS-020 | [BE] RedemptionTransaction — entity, migration V005, providerName enum | 3 | S3 | RS-003, RS-011 | BE2 |
| RS-021 | [BE] RedemptionOrchestrationService — validation, reservation, mode routing | 5 | S3 | RS-003, RS-013, RS-020 | BE2 |
| RS-022 | [BE] XtrmAdapter — submitPayout(), retry, VendorUnavailableException | 5 | S3 | RS-020, XTRM creds | BE3 |
| RS-023 | [BE] XoxodayAdapter — placeOrder(), retry, error handling | 5 | S3 | RS-020, Xoxoday creds | BE3 |
| RS-024 | [BE] RedemptionController — POST /requests, GET /requests, GET /requests/{id} | 3 | S3 | RS-021 | BE2 |
| RS-025 | [BE] RedemptionController — POST /{id}/approve, POST /{id}/reject | 2 | S3 | RS-021 | BE2 |
| RS-026 | [FE] RedemptionDrawer — amount input, SLA display, processing mode description | 5 | S3 | RS-016, RS-014 | FE1 |
| RS-027 | [FE] Redemption submission — useSubmitRedemption, success/error toast | 3 | S3 | RS-026 | FE1 |
| RS-028 | [QA] RedemptionOrchestration integration tests — INSTANT, BATCH, APPROVAL flows | 3 | S3 | RS-021, RS-022, RS-023 | QA+BE2 |
| RS-029 | [BE] XtrmWebhookService — HMAC verify, COMPLETED/FAILED/CANCELLED, idempotency | 5 | S4 | RS-022 | BE3 |
| RS-030 | [BE] XoxodayWebhookService — HMAC verify, FULFILLED/FAILED, idempotency | 5 | S4 | RS-023 | BE3 |
| RS-031 | [BE] Webhook controllers — POST /webhook/xtrm, POST /webhook/xoxoday | 2 | S4 | RS-029, RS-030 | BE3 |
| RS-032 | [QA] Webhook integration tests — idempotency, invalid HMAC, DB state assertions | 5 | S4 | RS-029, RS-030 | QA+BE3 |
| RS-033 | [BE] Transaction history API — paginated, filtered, export endpoint | 3 | S4 | RS-020 | BE2 |
| RS-034 | [FE] TransactionHistory page — table, status badges, date filter, export | 5 | S4 | RS-033 | FE1 |
| RS-035 | [BE] Observability — MDC fields, Micrometer counters, structured log statements | 3 | S4 | RS-029, RS-030 | BE1+BE3 |
| RS-036 | [BE] Notifications — all redemption lifecycle events to REWARDS category | 3 | S4 | RS-029, RS-030 | BE2 |
| RS-037 | [FE+BE] Payout SLA display on catalog item and redemption confirmation | 2 | S4 | RS-026, RS-014 | FE1+BE2 |
| RS-038 | [BE] RedemptionReturn — entity, migration V006, one-to-one with transaction | 3 | S5 | RS-020 | BE2 |
| RS-039 | [BE] ReturnsService — full lifecycle, return window validation, adapter call | 5 | S5 | RS-038, RS-023 | BE2 |
| RS-040 | [BE] XoxodayAdapter.submitReturn() — return API call, VendorReturnRejectedException | 3 | S5 | RS-023, RS-038 | BE3 |
| RS-041 | [BE] XoxodayWebhookService — RETURN_CONFIRMED and RETURN_FAILED events | 3 | S5 | RS-030, RS-038 | BE3 |
| RS-042 | [BE] Returns API — all 5 endpoints: submit, list, approve, reject, cancel | 3 | S5 | RS-039 | BE2 |
| RS-043 | [FE] Return request flow — submit from history, status tracking, cancel | 3 | S5 | RS-034, RS-042 | FE2 |
| RS-044 | [FE] Admin return approval queue — pending list, approve/reject with reason | 3 | S5 | RS-042 | FE2 |
| RS-045 | [BE] Return notifications — all return lifecycle events | 2 | S5 | RS-041, RS-042 | BE2 |
| RS-046 | [BE] Redemption rate analytics — rate by currency, catalog item, tier, region | 5 | S5 | RS-033 | BE2 |
| RS-047 | [BE] Unredeemed balance report — outstanding liability by currency type | 3 | S5 | RS-003 | BE2 |
| RS-048 | [FE] Analytics dashboard — redemption rate charts, unredeemed balance, filters | 5 | S5 | RS-046, RS-047 | FE2 |
| RS-049 | [QA] Returns integration tests — window, rejection, wallet credit on confirm only | 3 | S5 | RS-039, RS-041 | QA+BE2 |

| Track | Stories | Total Points | Sprints |
| --- | --- | --- | --- |
| Track A — Must Ship (Wallet, Catalog, Redemption, Webhooks, History) | RS-001 to RS-037 | 37 stories · 100 points | Sprints 1–4 |
| Track B — Returns and Analytics | RS-038 to RS-049 | 12 stories · 42 points | Sprint 5 |
| Total | 49 stories | 142 points | Sprints 1–5 |

# 6. Milestones

| Milestone | Week | Definition | Sign-Off |
| --- | --- | --- | --- |
| M0: Kick-Off | Week 0 | BRD approved, team assembled, vendor contacts made | Product Manager |
| M1: Technical Design Complete | End Week 2 | Entity designs approved, API contracts signed off, vendor API reviews complete, sprint backlog created, staging environment ready | Tech Lead + Product Manager |
| M2: Wallet Engine Live in Staging | End Sprint 1 (Week 4) | RewardWallet + LedgerEntry operational. WalletService unit tests passing. Balance APIs returning correct data. Persistent nav widget deployed. | Product Manager |
| M3: Catalog and Config Live | End Sprint 2 (Week 6) | Currency-aware catalog browsing correct. Client Admin configurator working. Regional filtering applied. Shortfall display correct. | Product Manager |
| M4: End-to-End Redemption Live | End Sprint 3 (Week 8) | Full redemption submission working against XTRM and Xoxoday sandboxes. Balance reserved on submission. APPROVAL_REQUIRED held before vendor. | Product Manager + Tech Lead |
| M5: Track A Complete | End Sprint 4 (Week 10) | Webhook processing live. Ledger finalised on COMPLETED. Transaction history working. Notifications sending. Observability in place. All Track A acceptance criteria met. | Product Manager |
| M6: Track B Complete | End Sprint 5 (Week 12) | Returns flow end-to-end. Admin approval queue working. Analytics dashboard showing redemption rates. Return notifications sending. | Product Manager |
| M7: Production Release | End Sprint 6 (Week 14) | Go-live checklist complete. Security review signed off. Performance validated. Feature live in production. Support briefed. | Product Manager + Delivery Lead |

# 7. Quality Gates

## 7.1 Definition of Done — Every Story

- Code reviewed and approved by at least one peer (two reviewers for data model or webhook handler changes)

- Unit tests written and passing — 60% line / 50% branch minimum per JaCoCo

- No tenantId, OffsetDateTime, or auto-increment ID violations (checked in code review)

- Every API endpoint has @RequiresPermission annotation — no exceptions

- Every UI action with side effects has a PermissionGate wrapper

- Every new Flyway migration has an index on client_id

- Story acceptance criteria verified and accepted by Product Manager

## 7.2 Definition of Done — Production Release

- All 49 stories accepted by Product Manager

- Full E2E Playwright suite passing — all happy paths and key error states

- Security review completed — tenant isolation, HMAC webhook auth, permission gates, no credentials in logs

- Performance validated — wallet balance reads and concurrent webhook processing under load

- All 12 go-live checklist items signed off (Section 8)

- Rollback plan documented: feature flag OFF removes all UI access; migrations are forward-only (no breaking schema changes in any sprint)

- Release notes approved by Product Manager

- Support team briefed on new feature, edge cases, and escalation path

# 8. Go-Live Checklist

| # | Item | Owner | Status |
| --- | --- | --- | --- |
| 1 | Feature flag redemption_store configured in production — all three tiers enabled | DevOps |  |
| 2 | All Flyway migrations V001–V009 applied to production database and validated | DevOps |  |
| 3 | Indexes confirmed on client_id and all FK columns in production | DevOps |  |
| 4 | All 11 permission keys seeded in production permissions table | Backend Lead |  |
| 5 | Default role-permission mappings configured for all 11 new permissions | Product Manager |  |
| 6 | XTRM production API key loaded into production secrets manager | DevOps |  |
| 7 | Xoxoday production API key loaded into production secrets manager | DevOps |  |
| 8 | XTRM webhook signing secret loaded into production secrets manager | DevOps |  |
| 9 | Xoxoday webhook signing secret loaded into production secrets manager | DevOps |  |
| 10 | XTRM webhook URL registered in XTRM dashboard pointing to /api/v1/redemption/webhook/xtrm | Backend Lead |  |
| 11 | Xoxoday webhook URL registered in Xoxoday dashboard pointing to /api/v1/redemption/webhook/xoxoday | Backend Lead |  |
| 12 | Monitoring alerts configured for: webhook processing failures, ledger mutation errors, wallet balance inconsistency | DevOps |  |

# 9. Risks and Mitigations

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| XTRM or Xoxoday sandbox credentials delayed | Medium | High — blocks Sprint 1 vendor adapter stories (RS-022, RS-023) | Escalate to vendor account managers in Pre-Sprint Week 1. If still delayed by Sprint 3 start, stub adapters with mocks and continue; integrate real credentials when available. |
| Vendor webhook schema differs from documentation | Medium | Medium — requires adapter rework in Sprint 4 | Schedule dedicated API technical review sessions with both vendors during Pre-Sprint. Build adapters with schema validation that logs mismatches. |
| Wallet balance race condition under concurrent redemptions | Low | High — ledger inconsistency | Pessimistic write lock on reserve(). Stress test concurrent wallet writes in Sprint 6 performance validation. Optimistic locking as secondary defence. |
| Open Questions #2, #3, #5 unresolved by required sprint | Medium | Medium — blocks affected stories | Delivery Lead to flag at each sprint retrospective. No story pointing for stories blocked on unresolved open questions. |
| Xoxoday return API not available or undocumented | Low | High — blocks entire Track B returns flow | Confirm return API availability and schema during Pre-Sprint Xoxoday API review. If unavailable, Track B returns scope is descoped to Phase 2. |
| Sprint 5 scope underestimated (42 points in one sprint) | Medium | Medium — Track B slips | Track B is independent of the M7 production release. If Sprint 5 overruns, split into Sprint 5a and 5b without blocking the release date. |
| Security finding in Sprint 6 review | Low | High — could delay production release | Run a lightweight pre-review in Sprint 4 on webhook handlers and tenant isolation. Resolve findings in Sprint 5 buffer. Full review in Sprint 6 as a gate. |